## Sheet1
Num | ID | Summary | Pasos | Expected Result | Obtained Result | Status | Notes
1 | PRO001 | Products home | 1. The user clicks products home | 1. The products home is correctly |  | KO | No aparece la funcionalidad de "ES MENU" en el listado principal: PRO004.jpg
2 | PRO002 | Products: Create, mandatory fields | 1. The user clicks "Nuevo producto" 2. Fills the mandatory fields 3. Clicks "Crear" | 1. The product is created. |  | KO | 1. The IA is not working https://drive.google.com/file/d/1sJVvwxAjHen83ICnAAqa12qjxpVXmmTu/view?usp=drive_link 15/04/26: SOLUCIONADO: ProductsPage.tsx - se reemplazaron los alert() por un estado aiError con mensaje inline. Cuando el error es por falta de API key de OpenAI, se muestra 'La IA no está configurada. Ve a Configuración → Configuración de IA para añadir tu API key'. 17/04/26: Aparece un INTERNAL SERVER ERROR: PRO003.jpg
2 | PRO002 | Products: Create , all fields | 1. The user clicks "Nuevo producto" 2. Fills the all fields 3. Clicks "Crear" | 1. The product is created. |  | KO | 1. The IA is not working https://drive.google.com/file/d/1sJVvwxAjHen83ICnAAqa12qjxpVXmmTu/view?usp=drive_link 15/04/26: SOLUCIONADO: ProductsPage.tsx - se reemplazaron los alert() por un estado aiError con mensaje inline. Cuando el error es por falta de API key de OpenAI, se muestra 'La IA no está configurada. Ve a Configuración → Configuración de IA para añadir tu API key'. 17/04/26: Aparece un INTERNAL SERVER ERROR: PRO003.jpg
10 | PRO010 | Products: Cancel creation | 1. The user clicks "Nuevo producto" 2. Cancel the operation | 1. The operation is cancelled. |  | OK
3 | PRO003 | Products: Modify | 1. The user clicks icon pencil | 1. The product is modified. |  | BL | 1. The IA is not working https://drive.google.com/file/d/1sJVvwxAjHen83ICnAAqa12qjxpVXmmTu/view?usp=drive_link 15/04/26: SOLUCIONADO: Mismo fix que PRO002. El feedback de error de IA ya no usa alert() sino un mensaje inline visible en el modal del producto. 17/04/26: Bloqueada por no poder crear productos: PRO003.jpg
11 | PRO011 | Products: Modify ,cancel | 1. The user clicks icon pencil 2. Cancel the operation | 1. The operation is canceled. | 1. The operation is canceled. | OK
4 | PRO004 | Products: Delete | 1. The user clicks icon garbage | 1. The product is deleted. | 1. The product is deleted. | OK
12 | PRO012 | Products: Delete, cancel | 1. The user clicks icon garbage 2. Cancel the operation | 1. The operation is cancelled. | 1. The operation is cancelled. | OK
5 | PRO005 | Products: Modify | 1. The user clicks in a product 2. Modify the price | 1. The price is updated. |  | PTE | ¿Dónde se ve este cambio?
6 | PRO006 | Products: Filter, All categories, menus | 1. The user chooses a categorie | 1. The products of the categorie selected, are shown. | 1. The products of the categorie selected, are shown. | OK
7 | PRO007 | Products: Search | 1. The user searches a product | 1. The sought product is displayed | 1. The sought product is displayed | OK
8 | PRO008 | Products: Show next page | 1. The user clicks icon next page (there are 20 products) | 1. Next products are displayed. |  | BL | The button is not working https://drive.google.com/file/d/1NEVph-7690Gw4j16HQBRHo9CDe9CLUbT/view?usp=drive_link 15/04/26: Fixed: removed products?.meta.page and products?.meta.limit from useEffect deps. These caused the effect to re-run on page change and reset to page 1 via the debounced setTimeout. Now uses useRef to track current page for the auto-refresh interval. 17/04/26: Bloqueada por no poder crear productos: PRO003.jpg
9 | PRO009 | Products: Shaw previous page | 1. The user clicks icon previous page | 1. Previous next are displayed. |  | BL | The button is not working https://drive.google.com/file/d/1NEVph-7690Gw4j16HQBRHo9CDe9CLUbT/view?usp=drive_link 15/04/26: Fixed as part of PRO008: same root cause resolved. 17/04/26: Bloqueada por no poder crear productos: PRO003.jpg
13 | PRO013 | Products: Error without mandatory field | 1. The user create a product without mandatory parameter | 1. An error is shown. | 1. An error is shown. | OK
14 | PRO014 | Products: Error with an error in a field | 1. The user create a product with an error in a field | 1. An error is shown. |  | BL | 17/04/26: Bloqueada por no poder crear productos: PRO003.jpg