## Sheet1
Num | ID | Summary | Pasos | Expected Result | Obtained Result | Status | Notes
1 | MEN001 | Menus: home | 1. The user sees the menus' home | 1. The menus' home is correctly. | 1. The menus' home is not correctly. | KO | Falta la tilde. https://drive.google.com/file/d/1eJt6l1D_V6LJmak01KkOlF4mEOJ6GUXs/view?usp=drive_link NOTA: comportamiento diferente a otras pantallas, aquí el botón "Continuar" no se activa, si no está relleno el campo obligatorio "Nombre". HAY QUE UNIFICAR EL COMPORTAMIENTO DE LAS PANTALLAS.
2 | MEN002 | Menus: Create first menu, mandatory parameters | 1. The user clicks"+ Crear Primer Menú" 2. The user fills mandatory fields. 3. The user clicks "Crear menú" | 1. The menu is created. | 1. The menu is created. | OK | Se crea el menú, xq lo veo en la sección de Productos, pero en "menus" no se lista, ni parece que haya ninguno. 15/04/26: SOLUCIONADO: Backend owner.service.ts - la creación de product + menuDefinition se envolvió en una $transaction de Prisma para garantizar atomicidad. Si menuDefinition.create falla, el product también se revierte. Además MenusPage.tsx ahora muestra el error en el modal en lugar de un alert().
3 | MEN003 | Menus: Create first menu, all parameters | 1. The user clicks"+ Crear Primer Menú" 2. The user fills all fields. 3. The user clicks "Crear menú" | 1. The menu is created. | 1. The menu is not created. | KO | 16/04/26: Se ha introducido un IVA con 4 digitos, y aparece "INTERNAL SERVER ERROR":menu002.jpg
4 | MEN004 | Menus: Create first menu, cancel | 1. The user clicks"+ Crear Primer Menú" 2. The user fills all fields. 3. The user clicks "Cancelar" | The operation is cancelled. | The operation is cancelled. | OK
5 | MEN005 | Menus: Create new menu, mandatory parameters. | 1. The user clicks"+ Crear nuevo Menú" 2. The user fills the fields. 3. The user clicks "Crear menú" | 1. The menu is created. | 1. The menu is created. | KO
6 | MEN006 | Menus: Create new menu, all parameters. | 1. The user clicks"+ Crear nuevo Menú" 2. The user fills the fields. 3. The user clicks "Crear menú" | 1. The menu is created. | 1. The menu is created. | KO | 16/04/26: Se ha modificado un IVA con 4 digitos, y aparece "INTERNAL SERVER ERROR":menu002.jpg
7 | MEN007 | Menus: Create new menu, cancel | 1. The user clicks"+ Crear nuevo Menú" 2. The user fills the fields. 3. The user clicks "Cancelar" | The operation is cancelled. | The operation is cancelled. | OK
8 | MEN008 | Menus: Modify | 1. The user selects a menu. 2. The user modify fields 3. The user clicks "Guardar cambios" | 1. The menu is modified. | 1. The menu is not modified. | KO | 16/04/26: Se ha modificado un IVA con 4 digitos, y aparece "INTERNAL SERVER ERROR":menu002.jpg
9 | MEN009 | Menus: Modify, cancel | 1. The user selects a menu. 2. The user modify fields 3. The user clicks "Cancelar" | The operation is cancelled. | The operation is cancelled. | OK
10 | MEN010 | Menus: Delete | 1. The user selects a menu. 2. Clicks the garbage icon of a menu 3. Clicks "Confirmar! | 1. The menu is deleted. | 1. The menu is deleted. | OK
11 | MEN011 | Menus: Delete, cancel | 1. The user selects a menu. 2. Clicks the garbage icon of a menu 3. Clicks "Cancelar" | The operation is cancelled. | The operation is cancelled. | OK